## Daily Report
Bahar Energy Operatng Company Limited
DAILY OPERATIONS REPORT
REPORT: | 4 |  | SITE: | #REF! |  | WELL : | #REF! |  | RIG: | #REF! |  | CONTRACTOR: |  |  | #REF!
REPORT DATE: | 2012-08-22 |  |  | START DATE: |  | #REF! |  | DAYS FROM OPS START: |  |  |  | 4.5 Days + |  | DAYS ON LOCATION: |  |  | #REF! |  | AFE NUMBER: |  | #REF!
GL-MSL(m) |  | #REF! |  | RT to GRD LEVEL (m): |  | #REF! | LATITUDE: |  | #REF! |  |  |  | LONGITUDE: |  | #REF! |  |  | Wellbore Max Angle: |  |  | 1.32
06:00 DEPTH (m): | 234 |  | 24:00 DEPTH-MDBRT: |  | 234 | TVD (m BRT): |  | 234 | Previous Depth (m): |  |  | 234 |  | PROGRESS (m): |  |  | 0 |  | HOLE SIZE (in): |  | 17.5
Casing Size: | 13 3/8" |  | Casing (MD): |  | 233 | Casing (TVD): |  | 233 | Next Casing Size: |  |  | 9.625" | Next Casing (MD): |  |  | 1960 |  | Next Casing (TVD): |  |  | 1918
Formation: |  |  | Absheron |  |  | Lithology: |  |  | 100% Shale |  |  |  |  | Formation top @: |  |  | Surface
Drilling Superintendent: | [5 empty] | Wellsite Geologist: |  |  | Hikmet Janbaghishov |  |  |  |  | Operations DE:
Drilling Supervisor: |  |  | Perit ATALAY |  |  | Completion Supervisors: | [7 empty] | Senior DE: |  |  | Samir Gozalov
Night Drilling Supervisor: |  |  | M. Onur ERTURK |  |  | Material Coordinator: | [7 empty] | Drilling Manager: |  |  | Navai Mamedov
Operations Summary (Last 24 hours) |  |  |  | WOC. N/D previous BOP stack, N/U current wellhead.
Current Status: |  |  |  | Work on wellhead.
24 Hour Forecast (00:00 - 24:00) |  |  |  | RIH, Drill out cement. POOH.
WEATHER |  |  | WIND (kt) |  | SPEED |  | DIR | TEMP (c) |  | 27-30
13-18
COST US$: |  | DAILY COST: |  | 125642.83 |  | TOTAL COST TO DATE: |  | 924286.62 |  | DAILY MUD COST: | [6 empty] | CUMULATIVE MUD COST:
HSE and Well Control
Safety & Environmental Issues: |  |  | None to Report | [10 empty] | SCR DEPTH (ft mdbrt) - (ppg)
Last Recorded Incident date: Recorded Incident |  |  |  | N/A |  | Last Safety Meeting: |  |  | 23.08.2012 |  |  |  |  | PUMP #1 |  |  |  | PUMP #2
LOT TVD (m): |  |  | BHP: |  | MAASP: |  | LOT EMW (sg): |  |  | Test Pressure: |  |  |  | SCR |  |  |  | SCR
Last Csg Test Press: |  |  |  | Last BOP Pressure Test: |  |  | Next BOP Press Test: | [6 empty] | psi |  |  |  | psi
Time Breakdown 00:00 hrs to 24:00 hrs
FROM | TO |  | HOURS | PHASE | TASK | ACTIVITY | CODE | NPT | DETAILS OF OPERATION
00:00 | 03:30 |  | 3.5 | SURF | DRILL | DRL | P |  | Drill 17 12" hole from 216 m to 234 m. WOB: 2 T, Flow Rate: 960 gpm, RPM: 100, SPP: 1400 psi
03:30 | 4:30 |  | 1 | SURF | CLEAN | CIR | P |  | Circulate to clean hole prior to wiper trip.
4:30 | 7:00 |  | 2.5 | SURF |  |  | P |  | Wiper trip to 22 m. Observe overpull 8t at 168 m and 5t at 142 m. Reciprocate the string, OK. Start RIH.
7:00 | 9:00 |  | 2 | SURF |  |  | P |  | Circulation prior to POOH. Spot 63 bbl HI-VIS on bottom .
9:00 | 12:00 |  | 3 | SURF |  |  | P |  | POOH, no overpull. L/D BHA and Slb tools, B/O 17 1/2" bit. ( Dull: 1-1-WT-A-E-I-NO-TD)
12:00 | 12:30 |  | 0.5 | SURF |  |  | P |  | R/U 13 3/8"Casing tools. Conduct pre-job safety meeting prior to 13 3/8" casing running.
12:30 | 17:00 |  | 4.5 | SURF |  |  | P |  | P/U first joint 13 3/8"csg with float shoe, fill it up w/mud for fuction test shoe, OK. Run 19 joints 13 3/8" K-55 #54.5 BTC casings. Tag at 234 m w/2 t, OK. Set shoe at 232m.
17:00 | 18:00 |  | 1 | SURF |  |  | P |  | Preparation for cement job. M/U cementing head and cementing lines, test lines,OK. Circulation at bottom prior to cement job.
18:00 | 20:00 |  | 2 | SURF |  |  | P |  | Conduct pre-job safety meeting prior to cement job. Fill lines w/ 10 bbl water, test lines to 2000 psi for 5 minutes, OK. Pump 40 bbls preflush fluid as a spacer, drop bottom plug. Pump 139 bbl 12 ppg lead slurry w/ 4.5 bpm rate. Pump 47 bbl 15.4 ppg tail slurry w/ 4 bpm rate. Drop top plug, displace it w/ 110 bbl mud. Bump the plug at 900 psi. Test the plug to 1350 psi for 5 minutes, OK. Observe and dump 50 bbl cement at surface. Check any returns, no returns. Full circulation during cement job.
20:00 | 0:00 |  | 4 | SURF | CASE | WOC | P |  | WOC.
|  | Total Hours |  | 24 | NPT:
Time Breakdown 24:00 hrs to 06:00 hrs update
FROM | TO |  | HOURS | PHASE | TASK | ACTIVITY | CODE | NPT | DETAILS OF OPERATION
0:00 | 1:00 |  | 1 | SURF | BOPSUR | TSTPRS | P |  | Preparation for pressure test. Conduct safety meeting prior to wellhead tests.
1:00 | 4:00 |  | 3 | SURF | BOPSUR | TSTPRS | P |  | Function test of Annular and RAM BOP, OK. Test choke manifold to 500 psi and 2000 psi, OK. Test blind ram to 500 psi and 1000 psi, OK. Test Annular BOP and Ram Type BOP, failure. Check the lines, no leakage observed. Pull test tool and re-run. Test Annular BOP to 500 psi and 1500 psi, OK. Test pipe ram to 2000 psi, OK.
4:00 | 6:00 |  | 2 | SURF | BOPSUR | NU | P |  | N/U conductor, weld it and work on wellhead. Set wear bushing.
|  | Total Hours |  | 6 | NPT
Survey and Formation Tops
Last 24hrs Survey:
No. | SURVEY DEPTH (m) |  |  | INC. (deg) |  | AZI. (deg) |  | TVD (mbrt) |  | NORTHING |  |  |  | EASTING |  |  | VERT. SECTION |  |  | DLS
| 129 |  |  | 0.99 |  | 92.37 |  | 129
| 157 |  |  | 0.77 |  | 84.05 |  | 157
| 186 |  |  | 1.05 |  | 100.1 |  | 186
| 215 |  |  | 1.3 |  | 100.73 |  | 215
| 227 |  |  | 1.32 |  | 110.41 |  | 227
| 234 |  |  | 1.3 |  | 110 |  | 234
WOB RANGE (klbs) |  |  |  | MIN | [5 empty] | AVG | [8 empty] | PICK UP WEIGHT (Tlbs)
TORQUE (kftlbs) |  |  |  | MIN | [5 empty] | AVG | [8 empty] | ROTATING OFF BTM WEIGHT (Tlbs)
RPM RANGE |  |  |  | MIN | [5 empty] | AVG | [8 empty] | SLACK OFF WEIGHT Tlbs)
BACKGROUND TOT. GAS(%) | [6 empty] | TRIP GAS (% OVER B/GROUND) | [11 empty] | CONN. GAS (% OVER B/GROUND)
MAX DRILLED GAS (%) | [6 empty] | DEPTH |  | m | DITCH MAGNET RECOVERY (lbs)
Provisional Formation Tops
NAME |  |  |  | TOP (mdbrt) |  |  | TOP (tvd ss) |  |  | NAME |  |  |  | TOP (mdbrt) |  |  | TOP (tvd ss)
Absheron
MUD |  | TYPE |  |  | MW (ppg / SG) |  |  | VISCOSITY (sec) |  | PV (cP) |  | YP (lbs/ft2) |  | GELS 10sec/10min |  |  | CHLORIDES (mg/l) |  |  | SAND (%)
|  | KCl PHPA Polymer |  |  | 1.08 |  |  | 110 |  | 44 |  | 40 |  | 2/5 |  |  | 29000 |  |  | 0.1
|  | FLUID LOSS (mls) |  |  | DAILY COST (US) |  |  | TOT. COST (US) |  | pH |  | VOL. ADDED |  |  | VOLUME LOST |  |  | ANN. VEL. DP/DC ft / min |  |  | ECD
|  | 8 | [7 empty] | 9
K2SO4 (%)
CASING DATA |  | 13-3/8" |  |  |  | 9-5/8" |  |  |  | 7"
|  | m mdbrt |  | m tvdbrt |  | m mdbrt |  | m tvdbrt |  | m mdbrt |  |  | m tvdbrt |  | m mdbrt |  | m tvdbrt |  | m mdbrt |  | m tvdbrt
|  | 233 |  | 233
|  | WT (lbs/ft) |  | CONN |  | WT (lbs/ft) |  | CONN |  | WT (lbs/ft) |  |  | CONN |  | WT (lbs/ft) |  | CONN |  | WT (lbs/ft) |  | CONN
|  | 54.5 |  | BTC
Remarks
CURRENT BIT RUN |  | BIT NO. |  | MANUFACTURER |  |  |  | TYPE |  | IADC |  |  | NOZZLES / TFA |  |  |  | SER. NO. |  |  | SIZE (in)
|  | DEPTH IN |  | TOTAL HRS on Bottom |  | Drilling K-revs |  | TOT. METERS |  | 24HR METERAGE |  |  |  | WOB |  | RPM |  | FLOW (gpm) |  | PRESSURE (psi)
PULLED BIT INFO |  | DEPTH IN |  | DEPTH OUT |  | METERAGE |  | HRS | ROP | Drilling K-revs |  | GRADING |  | IN | OUT | DULL | LOC | BRG | GAUGE | CHAR | REAS
|  | 0 |  | 234 |  | 234 |  | 41 | 5.8 |  |  |  |  | 1 | 1 | WT | A | E | I | NO | TD
Remarks
LAST BIT RUN |  | BIT NO. |  | MANUFACTURER |  |  |  | TYPE |  | IADC |  |  | NOZZLES / TFA |  |  |  | SER. NO. |  |  | SIZE (in)
|  | 1 |  | Smith |  |  |  | XR+ |  | 1-1-5 |  |  | 4 x 22/32 |  |  |  | PX3727 |  |  | 17.5
|  | DEPTH IN |  | DEPTH OUT |  | METERAGE |  | HRS | ROP | Drilling K-revs |  | GRADING |  | IN | OUT | DULL | LOC | BRG | GAUGE | CHAR | REAS
|  | 0 |  | 234 |  | 234 |  | 41 | 5.8 |  |  |  |  | 1 | 1 | WT | A | E | I | NO | TD
Remarks
CURRENT BHA DETAILS |  | BHA NO: |  |  | LENGTH: |  |  | EFFECTIVE WT : |  |  |  |  | BHA WT: |  |  |  | WT BELOW JAR:
BULKS |  | MATERIAL TYPE | [8 empty] | MATERIAL TYPE
|  | Barite (1500 kg) | [5 empty] | 73 |  |  | Diesel Received | [9 empty] | ltrs
|  | Bentonite (1000 kg) | [5 empty] | 1 |  |  | Diesel Used | [6 empty] | 2000 |  |  | ltrs
|  | Bentonite (25 kg) | [5 empty] | 80 |  |  | Diesel Remaining | [6 empty] | 50000 |  |  | ltrs
|  | CaCO3 (F) (25 kg) | [5 empty] | 80
|  | Caustic Soda (25 kg) | [5 empty] | 35
|  | HJN 102 (25 kg) | [5 empty] | 18
|  | HY-202 (80 kg) | [5 empty] | 80 |  |  | Water Truck | [8 empty] | 75 bbls / load
|  | KCl (1000 kg) | [5 empty] | 17 |  |  | Waste Water hauled in / total | [8 empty] | 75 bbls / load
|  | KPAM (25 kg) | [5 empty] | 166 |  |  | Waste Water hauled out / total | [8 empty] | 15 tons / load
|  | Mica (F) (25 kg) | [5 empty] | 160 |  |  | Waste Sludge hauled out / total | [8 empty] | 22 tons / load
|  | NH4H PAN (25 kg) | [5 empty] | 40 |  |  | Pre mix mud hauled out to Work Over Rig | [8 empty] | 75 bbls / load
|  | PAC LV (25 kg) | [5 empty] | 146
|  | PAC HV (25 kg) | [5 empty] | 93
|  | Quick-Thin (23 kg) | [5 empty] | 40
|  | RH4 (200 lt) | [5 empty] | 2
|  | Seal YT (F) (25 kg) | [5 empty] | 98
|  | Soda Ash (Na2CO3) (40 kg) | [5 empty] | 62
|  | Wallnut Fine (25 kg) | [5 empty] | 240
|  | Xanthan Gum D (25 kg) | [5 empty] | 115
|  | Citric Acid | [5 empty] | 20
Personnel On Site
DAY SHIFT OPERATION | [10 empty] | NIGHT SHIFT OPERATION
COMPANY NAME | [5 empty] | Man Power |  | Man Hours |  |  | COMPANY NAME | [7 empty] | Man Power |  | Man Hours
BEOC | [5 empty] | 2 |  | 8 |  |  | BEOC | [7 empty] | 1 |  | 12
Rig Personnel | [5 empty] | 22 |  | 324 |  |  | Rig Personnel | [7 empty] | 13 |  | 156
Mud Engineer | [5 empty] | 2 |  | 24 |  |  | Mud Engineer | [7 empty] | 1 |  | 12
Mud Logging | [5 empty] | 2 |  | 24 |  |  | Mud Logging | [7 empty] | 2 |  | 24
BJ Cementing | [7 empty] | 0 |  |  | BJ Cementing | [7 empty] | 2 |  | 24
Schlumberger E-Logging | [7 empty] | 0 |  |  | Schlumberger E-Logging | [9 empty] | 0
Schlumberger Directional Drilling | [7 empty] | 0 |  |  | Schlumberger Directional Drilling | [9 empty] | 0
Scientific Drilling International | [7 empty] | 0 |  |  | Scientific Drilling International | [9 empty] | 0
Coring | [7 empty] | 0 |  |  | Coring | [9 empty] | 0
ESP Personnel | [7 empty] | 0 |  |  | ESP Personnel | [9 empty] | 0
Fishing Tools | [7 empty] | 0 |  |  | Fishing Tools | [9 empty] | 0
Weatherford - Casing Running | [7 empty] | 0 |  |  | Weatherford - Casing Running | [9 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
[8 empty] | 0 | [12 empty] | 0
Total | [5 empty] | 28 |  | 380 |  |  | Total | [7 empty] | 19 |  | 228
Date of Last Record Loss Time Incident | [10 empty] | 24 Hrs Total Man Hours | [7 empty] | 608 |  | hrs.
Last Total Man Hours Record | [5 empty] | - |  | hrs. |  |  | Previous Total Man Hours | [7 empty] | 3616 |  | hrs.
[11 empty] | Total Man Hours from last LTI's | [7 empty] | 4224 |  | hrs.
0
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
0
Note on H33: P - Productive time N - Non-Productive Time C - Change of scope X - NPT during change of scope
Note on H49: P - Productive time N - Non-Productive Time C - Change of scope X - NPT during change of scope
Note on I33: CEMT --- Cementing - The failure of any and all aspects of a cementing job including, inappropriate setting times, channelling, and equipment failures DFAL --- Downhole Failures – The failure of any downhole equipment (except cementing equipment), including BHA, tool strings, drill or running string, tubing, casing, etc DPRB --- Downhole Problems – The failure of the wellbore (excluding stuck pipe) including influx control problems FLUD --- Fluids – Problems relating to wellbore fluids (drilling muds, completions fluids, etc) and their properties and constituents WAIT --- All unplanned waiting (excludes waiting which was part of the well plan, such as waiting for production to shut in a well prior to work commencing) RREP --- Rig Repairs – Time lost due to necessary work to the rig/primary unit working on the well including levelling the rig. SFAL --- Surface Equipment Failure – Problems relating to surface equipment (other than time lost repairing rig/primary), such as service company equipment (other than cement company equipment) and operator equipment STUC --- Stuck Pipe - All stuck pipe related problems (including stuck tool strings) UFAL --- Subsea Equipment Failure – All failures of subsea equipment including ROV and Diver equipment problems and seabed wellhead equipment HMAN --- Human Error – Problems caused by the way people work (lack of training, communication, etc) MISC --- ONLY TO BE USED IF NO OTHER CATEGORY CAN BE FOUND TO FIT THE SITUATION
Note on I49: CEMT --- Cementing - The failure of any and all aspects of a cementing job including, inappropriate setting times, channelling, and equipment failures DFAL --- Downhole Failures – The failure of any downhole equipment (except cementing equipment), including BHA, tool strings, drill or running string, tubing, casing, etc DPRB --- Downhole Problems – The failure of the wellbore (excluding stuck pipe) including influx control problems FLUD --- Fluids – Problems relating to wellbore fluids (drilling muds, completions fluids, etc) and their properties and constituents WAIT --- All unplanned waiting (excludes waiting which was part of the well plan, such as waiting for production to shut in a well prior to work commencing) RREP --- Rig Repairs – Time lost due to necessary work to the rig/primary unit working on the well including levelling the rig. SFAL --- Surface Equipment Failure – Problems relating to surface equipment (other than time lost repairing rig/primary), such as service company equipment (other than cement company equipment) and operator equipment STUC --- Stuck Pipe - All stuck pipe related problems (including stuck tool strings) UFAL --- Subsea Equipment Failure – All failures of subsea equipment including ROV and Diver equipment problems and seabed wellhead equipment HMAN --- Human Error – Problems caused by the way people work (lack of training, communication, etc) MISC --- ONLY TO BE USED IF NO OTHER CATEGORY CAN BE FOUND TO FIT THE SITUATION

## Time Breakdown
| REP # | DATE | FROM | TO |  | HOURS | PHASE | TASK | ACTIVITY | CODE | NPT | DETAILS OF OPERATION
1411400,5012PREMOBP | 1 | 2012-08-19 | 12:00 | 0:00 |  | 12 | PRE | MOB |  | P |  | Rig accepted at 12:00. Started preparation and mixing of mud. M/U and setback 6 stands HWDP, M/U 17 1/2" Smith Bit and BHA#1 (17 1/2" Bit, Bit Sub, 9" DC, 2 ea X/O, 6 ea 5" HWDP).
24114110,1253P | 2 | 2012-08-20 | 24:00 | 3:00 |  | 3 |  |  |  | P |  | Continue preparing and mixing mud.
2411410,1250,1458333333333330,5P | 2 | 2012-08-20 | 3:00 | 3:30 |  | 0.5 |  |  |  | P |  | Conduct safety meeting prior to spud and perform BOP drill.
2411410,14583333333333317:3014SURFP | 2 | 2012-08-20 | 3:30 | 17:30 | 17:30 | 14 | SURF |  |  | P |  | Spud the well and drill from surface to 66 m. WOB: 1-2 T, Flow Rate: 400-600 gpm, RPM: 60-65.
24114117:3018:000,5SURFDRILLCIRP | 2 | 2012-08-20 | 17:30 | 18:00 | 18:00 | 0.5 | SURF | DRILL | CIR | P |  | Circulate bottom up to clean hole.
24114118:0019:301,5SURFDRILLPULP | 2 | 2012-08-20 | 18:00 | 19:30 | 19:30 | 1.5 | SURF | DRILL | PUL | P |  | POOH for BHA change, no overpull. Observe bit partially ball up. B/O and clean up bit. L/D 1 ea 9"DC.
24114119:3021:001,5SURFDRILLBHPULDP | 2 | 2012-08-20 | 19:30 | 21:00 | 21:00 | 1.5 | SURF | DRILL | BHPULD | P |  | M/U Slb tools and new BHA (17 1/2"Bit + Bit Sub + 2 ea Telescope Bot Saver Sub + MWD + Telescope Top Saver Sub
24114121:0021:300,5SURFDRILLBHATSTP | 2 | 2012-08-20 | 21:00 | 21:30 | 21:30 | 0.5 | SURF | DRILL | BHATST | P |  | Test MWD at 110 strokes,OK.
24114121:3022:301SURFDRILLBHPULDP | 2 | 2012-08-20 | 21:30 | 22:30 | 22:30 | 1 | SURF | DRILL | BHPULD | P |  | M/U 17 1/2" Stabilizer + 9" NMDC and RIH to bottom. No tight hole.
24114122:3000:001,5SURFDRILLDRLP | 2 | 2012-08-20 | 22:30 | 00:00 | 00:00 | 1.5 | SURF | DRILL | DRL | P |  | Drill 17 1/2" hole from 66m to 76 m . WOB: 2 T, Flow Rate: 650 - 670gpm, RPM:75 SPP: 650 Psi
34114200:0000:0024SURFDRILLDRLP | 3 | 2012-08-21 | 00:00 | 00:00 | 00:00 | 24 | SURF | DRILL | DRL | P |  | Drill 17 12" hole from 76m to 216m. WOB: 2 T, Flow Rate: 960 gpm, RPM: 100, SPP: 1400 psi, Average ROP: 6.08 m
44114300:0003:303,5SURFDRILLDRLP | 4 | 2012-08-22 | 00:00 | 03:30 | 03:30 | 3.5 | SURF | DRILL | DRL | P |  | Drill 17 12" hole from 216 m to 234 m. WOB: 2 T, Flow Rate: 960 gpm, RPM: 100, SPP: 1400 psi
44114303:300,18751SURFCLEANCIRP | 4 | 2012-08-22 | 03:30 | 4:30 | 4:30 | 1 | SURF | CLEAN | CIR | P |  | Circulate to clean hole prior to wiper trip.
4411430,18750,2916666666666672,5SURFP | 4 | 2012-08-22 | 4:30 | 7:00 | 7:00 | 2.5 | SURF |  |  | P |  | Wiper trip to 22 m. Observe overpull 8t at 168 m and 5t at 142 m. Reciprocate the string, OK. Start RIH.
4411430,2916666666666670,3752SURFP | 4 | 2012-08-22 | 7:00 | 9:00 | 9:00 | 2 | SURF |  |  | P |  | Circulation prior to POOH. Spot 63 bbl HI-VIS on bottom .
4411430,3750,53SURFP | 4 | 2012-08-22 | 9:00 | 12:00 | 12:00 | 3 | SURF |  |  | P |  | POOH, no overpull. L/D BHA and Slb tools, B/O 17 1/2" bit. ( Dull: 1-1-WT-A-E-I-NO-TD)
4411430,50,5208333333333330,5SURFP | 4 | 2012-08-22 | 12:00 | 12:30 | 12:30 | 0.5 | SURF |  |  | P |  | R/U 13 3/8"Casing tools. Conduct pre-job safety meeting prior to 13 3/8" casing running.
4411430,5208333333333330,7083333333333334,5SURFP | 4 | 2012-08-22 | 12:30 | 17:00 | 17:00 | 4.5 | SURF |  |  | P |  | P/U first joint 13 3/8"csg with float shoe, fill it up w/mud for fuction test shoe, OK. Run 19 joints 13 3/8" K-55 #54.5 BTC casings. Tag at 234 m w/2 t, OK. Set shoe at 232m.
4411430,7083333333333330,751SURFP | 4 | 2012-08-22 | 17:00 | 18:00 | 18:00 | 1 | SURF |  |  | P |  | Preparation for cement job. M/U cementing head and cementing lines, test lines,OK. Circulation at bottom prior to cement job.
4411430,750,8333333333333332SURFP | 4 | 2012-08-22 | 18:00 | 20:00 | 20:00 | 2 | SURF |  |  | P |  | Conduct pre-job safety meeting prior to cement job. Fill lines w/ 10 bbl water, test lines to 2000 psi for 5 minutes, OK. Pump 40 bbls preflush fluid as a spacer, drop bottom plug. Pump 139 bbl 12 ppg lead slurry w/ 4.5 bpm rate. Pump 47 bbl 15.4 ppg tail slurry w/ 4 bpm rate. Drop top plug, displace it w/ 110 bbl mud. Bump the plug at 900 psi. Test the plug to 1350 psi for 5 minutes, OK. Observe and dump 50 bbl cement at surface. Check any returns, no returns. Full circulation during cement job.
4411430,83333333333333304SURFCASEWOCP | 4 | 2012-08-22 | 20:00 | 0:00 |  | 4 | SURF | CASE | WOC | P |  | WOC.
54114400,3958333333333339,5SURFCEMTWOCP | 5 | 2012-08-23 | 0:00 | 9:30 |  | 9.5 | SURF | CEMT | WOC | P |  | WOC. Disconect flow line, N/D BOP stack. Dump and clean sand tank, #2 mud tank, mix new mud. Prepare next BOP stack .
5411440,3958333333333330,56254SURFWHSURNDP | 5 | 2012-08-23 | 9:30 | 13:30 |  | 4 | SURF | WHSUR | ND | P |  | Cut 13 3/8"casing, N/D Diverter and bell nipple. Install and weld 13 3/8" x 3M Casing Head.
5411440,47916666666666724:0012,5SURFWHSURNUP | 5 | 2012-08-23 | 11:30 | 24:00 |  | 12.5 | SURF | WHSUR | NU | P |  | N/U 13 5/8" BOP stack, connect kill line, choke line and manifold..
64114500,04166666666666671SURFBOPSURTSTPRSP | 6 | 2012-08-24 | 0:00 | 1:00 |  | 1 | SURF | BOPSUR | TSTPRS | P |  | Preparation for pressure test. Conduct safety meeting prior to wellhead tests.
6411450,04166666666666670,1666666666666673SURFBOPSURTSTPRSP | 6 | 2012-08-24 | 1:00 | 4:00 |  | 3 | SURF | BOPSUR | TSTPRS | P |  | Function test of Annular and RAM BOP, OK. Test choke manifold to 500 psi and 2000 psi, OK. Test blind ram to 500 psi and 1000 psi, OK. Test Annular BOP and Ram Type BOP, failure. Check the lines, no leakage observed. Pull test tool and re-run. Test Annular BOP to 500 psi and 1500 psi, OK. Test pipe ram to 2000 psi, OK.
6411450,1666666666666670,252SURFBOPSURNUP | 6 | 2012-08-24 | 4:00 | 6:00 |  | 2 | SURF | BOPSUR | NU | P |  | N/U conductor, weld it and work on wellhead. Set wear bushing.
Note on K4: P - Productive time N - Non-Productive Time C - Change of scope X - NPT during change of scope
Note on L4: CEMT --- Cementing - The failure of any and all aspects of a cementing job including, inappropriate setting times, channelling, and equipment failures DFAL --- Downhole Failures – The failure of any downhole equipment (except cementing equipment), including BHA, tool strings, drill or running string, tubing, casing, etc DPRB --- Downhole Problems – The failure of the wellbore (excluding stuck pipe) including influx control problems FLUD --- Fluids – Problems relating to wellbore fluids (drilling muds, completions fluids, etc) and their properties and constituents WAIT --- All unplanned waiting (excludes waiting which was part of the well plan, such as waiting for production to shut in a well prior to work commencing) RREP --- Rig Repairs – Time lost due to necessary work to the rig/primary unit working on the well including levelling the rig. SFAL --- Surface Equipment Failure – Problems relating to surface equipment (other than time lost repairing rig/primary), such as service company equipment (other than cement company equipment) and operator equipment STUC --- Stuck Pipe - All stuck pipe related problems (including stuck tool strings) UFAL --- Subsea Equipment Failure – All failures of subsea equipment including ROV and Diver equipment problems and seabed wellhead equipment HMAN --- Human Error – Problems caused by the way people work (lack of training, communication, etc) MISC --- ONLY TO BE USED IF NO OTHER CATEGORY CAN BE FOUND TO FIT THE SITUATION