## Отчет
ID | AcReg | Start | End | Stn | Comment
400FH | SAU | 2023-06-11 22:40 | 2023-06-11 23:55 | HAM | 24-030-02-01 (36648 FH) |  |  |  | #NAME? | #NAME?
48 | SAU | 2023-06-12 00:25 | 2023-06-12 03:25 | HAM | 48 HRS |  |  |  | #NAME? | #NAME?
NDB | SAU | 2023-06-12 20:55 | 2023-06-12 21:55 | HAM | 34-001-01-SEU (15.06) NAVIGATION DATA BASE |  |  |  | #NAME? | #NAME?
500FH | SAU | 2023-06-12 21:55 | 2023-06-12 22:55 | HAM | 72-320-01-01, 72-320-02-01 (36671 FH) |  |  |  | #NAME? | #NAME?
300FH | SAU | 2023-06-13 21:20 | 2023-06-13 22:20 | HAM | 23-040-00-01 (36656 FH) |  |  |  | #NAME? | #NAME?
500FH | SAU | 2023-06-15 20:35 | 2023-06-16 00:35 | HAM | 25-006-05-SEU (36720 FH) GEVEN SEATS INSPECTION |  |  |  | #NAME? | #NAME?
15DY | SAU | 2023-06-16 01:35 | 2023-06-16 02:10 | HAM | 24-100-00-01, 38-040-00-01 (17.06) |  |  |  | #NAME? | #NAME?
ELT | SAU | 2023-06-16 20:55 | 2023-06-16 21:55 | HAM | 25-002-01-SEU (23.06) EMERGENCY LOCATOR TRANSMITTER ADT406 S SELF-TEST, 25-340-00-01 |  |  |  | #NAME? | #NAME?
FIRE | SAU | 2023-06-20 21:00 | 2023-06-21 | HAM | 26-450-00-01 - PN: 898052, SN: A30840580 (04.07) 26-450-00-01 - PN: 898052, SN: X-455632 (18.07) 26-450-00-01 - PN: 898052, SN: X-058172 (18.07) 26-450-00-01 - PN: 898052, SN: A30841431 (18.07) |  |  |  | #NAME? | #NAME?
FUEL | SAU | 2023-06-23 20:45 | 2023-06-23 22:20 | HAM | 73-010-01-01, 73-010-02-01 (36815 FH) |  |  |  | #NAME? | #NAME?
1000FH | SAU | 2023-06-23 22:20 | 2023-06-23 23:50 | HAM | 25-130-00-01, 25-005-07-SEU (36815 FH) |  |  |  | #NAME? | #NAME?
450FC | SAU | 2023-06-30 21:50 | 2023-06-30 23:30 | HAM | 25-160-00-01, 25-160-00-02 (16195 FC) |  |  |  | #NAME? | #NAME?
Задача что должно получиться:
[6 empty] | Находит текст в столбце F этого листа, сравнивает его со столбцом A листа TCs Title MT и подтягивает соответственное значение с листа TCs Title MT из колонки B | Находит текст в столбце F этого листа, сравнивает его со столбцом A листа TCs Title MT и подтягивает соответственное значение с листа TCs Title MT из колонки C | Находит текст в столбце F этого листа, сравнивает его со столбцом A листа TCs Title MT и подтягивает соответственное значение с листа TCs Title MT из колонки D
400FH | SAU | 2023-06-11 22:40 | 2023-06-11 23:55 | HAM | 24-030-02-01 (36648 FH) | Right IDG Oil Level | IF REQUIRED D00071 - TURB0NYC0IL600 (1 QT); O-ring - M83248-1-905 or M83485-1-905 or AS3208-05 (1 ea.) | 0.2
48 | SAU | 2023-06-12 00:25 | 2023-06-12 03:25 | HAM | 48 HRS | 48 HRS CHECK | N/A | 2
NDB | SAU | 2023-06-12 20:55 | 2023-06-12 21:55 | HAM | 34-001-01-SEU (15.06) | NAVIGATION DATABASE INSTALLATION | N/A | 1.5
500FH | SAU | 2023-06-12 21:55 | 2023-06-12 22:55 | HAM | 72-320-01-01, 72-320-02-01 (36671 FH) | Left Engine Fwd Sump, Aft Sump, AGB/TGB MCD or DMS detectors and scavenge screens Right Engine Fwd Sump, Aft Sump, AGB/TGB MCD or DMS detectors and scavenge screens | Packing P/N J221P028 (3 ea.); Seal P/N 335-299-401-0 (3 ea.) - on condition; Puller SPL-2447 Packing P/N J221P028 (3 ea.); Seal P/N 335-299-401-0 (3 ea.) - on condition; Puller SPL-2447 | 0,25 0,25
300FH | SAU | 2023-06-13 21:20 | 2023-06-13 22:20 | HAM | 23-040-00-01 (36656 FH) | Voice Recorder | N/A | 0.3
500FH | SAU | 2023-06-15 20:35 | 2023-06-16 00:35 | HAM | 25-006-05-SEU (36720 FH) | GEVEN SEATS INSPECTION (500 FH) | N/A | 12
15DY | SAU | 2023-06-16 01:35 | 2023-06-16 02:10 | HAM | 24-100-00-01, 38-040-00-01 (17.06) | Standby Power Control Unit (SPCU) Restore Waste Drain Ball-Valve | N/A P/N 2651-278-21 (1 ea.); Packing P/N M83461/1-238 (4 ea.); Gask-o-seal P/N 808048-4 (1 ea.); Gask-o-seal P/N 808048-1 (1 ea.); GREASE 22 P/N MIL-PRF-81322 (50 gr) | 0,1 4,06
ELT | SAU | 2023-06-16 20:55 | 2023-06-16 21:55 | HAM | 25-002-01-SEU (23.06), 25-340-00-01 | EMERGENCY LOCATOR TRANSMITTER ADT406 S SELF-TEST Power Megaphones Batteries | N/A Battery multipurpose 1 ½ volt P/N AA (6 ea.); for UR-SQQ (8 ea.) | 1 0,1
FIRE | SAU | 2023-06-20 21:00 | 2023-06-21 | HAM | 26-450-00-01 - PN: 898052, SN: A30840580 (04.07) 26-450-00-01 - PN: 898052, SN: X-455632 (18.07) 26-450-00-01 - PN: 898052, SN: X-058172 (18.07) 26-450-00-01 - PN: 898052, SN: A30841431 (18.07) | Portable Halon Fire Extinguishers Inspection Portable Halon Fire Extinguishers Inspection Portable Halon Fire Extinguishers Inspection Portable Halon Fire Extinguishers Inspection | N/A N/A N/A N/A | 0,1 0,1 0,1 0,1
FUEL | SAU | 2023-06-23 20:45 | 2023-06-23 22:20 | HAM | 73-010-01-01, 73-010-02-01 (36815 FH) | Replace the Left Engine Fuel Filter Replace the Right Engine Fuel Filter | D00601 SAE AMS 2518 (15 gr); D00623 MIL-PRF-6081 (15 gr) or D00672 Vaseline - Pure Mineral V V-P-236 (15 gr); Filter kit 65-90305-88 (1 ea.) D00601 SAE AMS 2518 (15 gr); D00623 MIL-PRF-6081 (15 gr) or D00672 Vaseline - Pure Mineral V V-P-236 (15 gr); Filter kit 65-90305-88 (1 ea.) | 0,7 0,7
1000FH | SAU | 2023-06-23 22:20 | 2023-06-23 23:50 | HAM | 25-130-00-01, 25-005-07-SEU (36815 FH) | Lavatory Waste Compartment Flapper Door and Spring and Access Door (WORK COVERED BY EO 737-25-034) LAVATORY WASTE COMPARTMENT FLAPPER DOOR, SPRING AND ACCESS DOOR INSPECTION | N/A N/A | 0,2 1
450FC | SAU | 2023-06-30 21:50 | 2023-06-30 23:30 | HAM | 25-160-00-01, 25-160-00-02 (16195 FC) | Inspect Fwd Cargo Compartment Panels/Liners Inspect Aft Cargo Compartment Panels/Liners | N/A N/A | 0,1 0,1

## TCs Title MT
TC | Title | Equipm/cons | Mhrs
23-040-00-01 | Voice Recorder | N/A | 0.3
24-030-01-01 | Left IDG Oil Level | IF REQUIRED D00071 - TURB0NYC0IL600 (1 QT); O-ring - M83248-1-905 or M83485-1-905 or AS3208-05 (1 ea.) | 0.2
24-030-02-01 | Right IDG Oil Level | IF REQUIRED D00071 - TURB0NYC0IL600 (1 QT); O-ring - M83248-1-905 or M83485-1-905 or AS3208-05 (1 ea.) | 0.2
24-100-00-01 | Standby Power Control Unit (SPCU) | N/A | 0.1
25-130-00-01 | Lavatory Waste Compartment Flapper Door and Spring and Access Door (WORK COVERED BY EO 737-25-034) | N/A | 0.2
25-160-00-01 | Inspect Fwd Cargo Compartment Panels/Liners | N/A | 0.1
25-160-00-02 | Inspect Aft Cargo Compartment Panels/Liners | N/A | 0.1
72-320-01-01 | Left Engine Fwd Sump, Aft Sump, AGB/TGB MCD or DMS detectors and scavenge screens | Packing P/N J221P028 (3 ea.); Seal P/N 335-299-401-0 (3 ea.) - on condition; Puller SPL-2447 | 0.25
72-320-02-01 | Right Engine Fwd Sump, Aft Sump, AGB/TGB MCD or DMS detectors and scavenge screens | Packing P/N J221P028 (3 ea.); Seal P/N 335-299-401-0 (3 ea.) - on condition; Puller SPL-2447 | 0.25
73-010-01-01 | Replace the Left Engine Fuel Filter | D00601 SAE AMS 2518 (15 gr); D00623 MIL-PRF-6081 (15 gr) or D00672 Vaseline - Pure Mineral V V-P-236 (15 gr); Filter kit 65-90305-88 (1 ea.) | 0.7
73-010-02-01 | Replace the Right Engine Fuel Filter | D00601 SAE AMS 2518 (15 gr); D00623 MIL-PRF-6081 (15 gr) or D00672 Vaseline - Pure Mineral V V-P-236 (15 gr); Filter kit 65-90305-88 (1 ea.) | 0.7
25-340-00-01 | Power Megaphones Batteries | Battery multipurpose 1 ½ volt P/N AA (6 ea.); for UR-SQQ (8 ea.) | 0.1
26-450-00-01 | Portable Halon Fire Extinguishers Inspection | N/A | 0.1
26-470-00-00 | Portable Water Fire Extinguisher Inspection | N/A | 0.1
38-040-00-01 | Restore Waste Drain Ball-Valve | P/N 2651-278-21 (1 ea.); Packing P/N M83461/1-238 (4 ea.); Gask-o-seal P/N 808048-4 (1 ea.); Gask-o-seal P/N 808048-1 (1 ea.); GREASE 22 P/N MIL-PRF-81322 (50 gr) | 4.06
05-001-01-SEU | 48 HOURS CHECK (48 HRS) |  | 3
08-001-01-SEU | Aircraft Weighing | N/A
20-001-01-SEU | CIRCUIT BREAKERS CYCLE | N/A | 1
21-001-07-SEU | Title: FUNCTIONAL CHECK OF CABIN PRESSURE SWITCH (PERFORM TOGETHER WITH TC 21-001-07-SEU) | N/A | 1
22-001-01-SEU | DIGITAL FLIGHT CONTROL SYSTEM (DFCS) OPERATIONAL TEST | N/A | 1.5
23-001-01-SEU | HF COMMUNICATION SYSTEM OPERATIONAL TEST | N/A | 1
23-002-01-SEU | FLIGHT INTERPHONE SYSTEM OPERATIONAL TEST | N/A | 1.5
23-003-01-SEU | COPY OF THE CVR DATA FOR CVR INTELLIGIBILITY CHECK | N/A | 2
23-004-01-SEU | COPY OF THE CVR DATA FOR DATA LINK RECORDING INTELLIGIBILITY CHECK | N/A | 2
24-001-07-SEU | ELECTRICAL POWER - GENERAL - CORROSION PROTECTION OF THE ELECTRICAL CONNECTORS IN THE MAIN WHEEL WELL | N/A | 10
25-001-01-SEU | AIRCRAFT INTERIOR CHECK | N/A | 10
25-002-01-SEU | EMERGENCY LOCATOR TRANSMITTER ADT406 S SELF-TEST | N/A | 1
25-003-01-SEU | VISUALLY CHECK LIFE VESTS AND EXPIRE DATE CONTROL | N/A | 6
25-004-04-SEU | AUTOMATED EXTERNAL DEFIBRILLATOR (AED) BATTERY PACK REPLACEMENT | N/A | 1
25-005-07-SEU | LAVATORY WASTE COMPARTMENT FLAPPER DOOR, SPRING AND ACCESS DOOR INSPECTION | N/A | 1
25-006-05-SEU | GEVEN SEATS INSPECTION (500 FH) | N/A | 12
25-007-05-SEU | GEVEN SEATS INSPECTION (1500 FH) | N/A | 3
25-008-05-SEU | GEVEN SEATS INSPECTION (3000 FH) | N/A | 3
25-009-05-SEU | GEVEN SEATS INSPECTION (5000 FH) | N/A | 2
26-001-04-SEU | RESTORE ENGINE FIRE BOTTLES BY HYDROSTATIC TESTING (OFF AIRCRAFT) | N/A
26-002-04-SEU | RESTORE APU FIRE BOTTLE BY HYDROSTATIC TESTING (OFF AIRCRAFT) | N/A
26-003-04-SEU | RESTORE CARGO COMPARTMENT FIRE BOTTLE BY HYDROSTATIC TESTING (OFF AIRCRAFT) | N/A
26-004-04-SEU | RESTORE PORTABLE HALON FIRE EXTINGUISHER (OFF AIRCRAFT) | N/A
26-005-07-SEU | Cargo Bay Smoke Detection – Equipment Cooling System Smoke Clearance Mode Operational Test for Cargo Smoke Detection | N/A | 4
27-001-07-SEU | AILERON BALANCE TAB FREEPLAY - CHECK | N/A | 4
27-002-07-SEU | Flight controls – Aileron and Aileron Trim Control System – Aileron Balance Tab Lubrication (PERFORM TOGETHER WITH TC 27-026-01-01/02-01) | N/A | 0.1
27-003-07-SEU | Horizontal stabilizer trim control system – ballscrew and ball nut detailed inspection | N/A | 4
27-004-07-SEU | Horizontal stabilizer trim control system – ballscrew and ball nut lubrication (PERFORM TOGETHER WITH TC 27-102-00-01) | N/A | 0.1
27-005-07-SEU | STABILIZER RESTORATION | N/A
31-001-01-SEU | OPERATIONAL TEST OF THE MASTER DIM AND TEST | N/A | 1
31-002-01-SEU | SYSTEM TEST OF THE FLIGHT DATA RECORDER SYSTEM. | N/A | 12
33-001-05-SEU | PHOTOLUMINESCENT FLOOR PATH MARKING CHECK FOR CRACKS AND PROPER INSTALLATION | N/A | 1
34-001-01-SEU | NAVIGATION DATABASE INSTALLATION | N/A | 1.5
34-002-01-SEU | STANDBY MAGNETIC COMPASS SYSTEM FUNCTIONAL TEST | N/A | 2
34-003-01-SEU | GLOBAL POSITIONING SYSTEM OPERATIONAL TEST | N/A | 1
35-001-04-SEU | RESTORE FLIGHT CREW OXYGEN CYLINDER BY HYDROSTATIC TESTING (OFF AIRCRAFT) | N/A
35-002-04-SEU | RESTORE PORTABLE OXYGEN CYLINDERS BY HYDROSTATIC TESTING (OFF AIRCRAFT) | N/A
36-001-07-SEU | INSPECTION OF THE ENGINE BLEED AIR 5TH STAGE VALVE | N/A
49-001-01-SEU | CT5ATP READOUT | N/A
57-001-06-SEU | LEFT WING OUTBOARD AFT FLAP TE WEDGE ASSEMBLY REPAIR - TAP-TEST INSPECTION | N/A | 1.5
71-001-07-SEU | GENERAL VISUAL INSPECTION OF THE CENTER LINK ASSEMBLY OF THE AFT ENGINE MOUNT
72-001-07-SEU L/H ENG | LEFT ENGINE - FAN BLADE DOVETAIL REPETITIVE ULTRASONIC INSPECTION | N/A
72-001-07-SEU R/H ENG | RIGHT ENGINE - FAN BLADE DOVETAIL REPETITIVE ULTRASONIC INSPECTION | N/A | 1.5
78-001-07-SEU | INTEGRITY TEST OF THE THRUST REVERSER UPPER LOCKING ACTUATOR | N/A | 1.5
48 HRS | 48 HRS CHECK | N/A | 2